## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## TM1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Excited | Neutral | Sad | Neutral | Neutral
1 | Research on project management software tools | Task Quality Evaluation (After Task Completed) | 8 | 7 | 9 | 7 | 8 | 8 | 6.5 | 2 | 2.3333 | Desmond Yap | Wong Ying, Duc | Through Discussion | Yes | 3 | Happy | 7.8333
| Estimated Task Priority（0-10） |  | 7 | 7 | 7 | 5 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 2 | 2 | 2 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 3 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 9 | 9
2 | Research on python web development framework | Task Quality Evaluation (After Task Completed) | 7 | 8 | 8 | 7 | 7 | 8 | 10 | 7.5 | 5.3333 | Hussain Khozema Kheriwala | Jeremy | Through Discussion | Yes | 5 | Happy | 7.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 8 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 6 | 7 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 6 | 8 | 7 | 7 | 7 | 7
3 | Research on recommender system | Task Quality Evaluation (After Task Completed) | 8 | 8 | 9 | 8 | 8 | 8 | 9 | 7.8333 | 5 | Jeremy Book | Hussain | Through Discussion | Yes | 5 | Happy | 8.1667
| Estimated Task Priority（0-10） |  | 8 | 10 | 9 | 10 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 8 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 5 | 7 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 6 | 8 | 9 | 6 | 7 | 9

## TM2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Depressed | Neutral | Neutral | Neutral | Neutral
1 | Complete Use Case Model | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 8 | 9 | 9 | 9 | 5.3333 | 2.6667 | Wong Ying | Hussain, Jeremy, Duc, Desmond | Through Discussion | Yes | 2 | Happy | 8.5
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 9 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 6 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 3 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 7 | 6 | 7
2 | Complete Project Proposal | Task Quality Evaluation (After Task Completed) | 8 | 8 | 9 | 8 | 8 | 8 | 9.5 | 8 | 4.1667 | Wong Ying | Hussain, Jeremy, Duc, Desmond | Through Discussion | Yes | 4 | Happy | 8.1667
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 8 | 9 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 6 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 6 | 7 | 8 | 8 | 7 | 7
3 | Produce Project Timeline | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 8 | 8 | 6.5 | 5 | Desmond Yap | - | Allocated by Team Leader | Yes | 5 | Happy | 8.1667
| Estimated Task Priority（0-10） |  | 8 | 8 | 7 | 8 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 6 | 7 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 4 | 4 | 8 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 9 | 8 | 7
4 | Update Wiki Page | Task Quality Evaluation (After Task Completed) | 8 | 8 | 7 | 9 | 9 | 7 | 7 | 2.5 | 1.5 | Ta Anh Duc | - | Allocated by Team Leader | Yes | 2 | Happy | 8
| Estimated Task Priority（0-10） |  | 7 | 8 | 7 | 6 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 2 | 3 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 | 8 | 8 | 7

## TM3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Neutral | Happy | Sad | Neutral
1 | Complete System Requirement Specification | Task Quality Evaluation (After Task Completed) | 8 | 7 | 8 | 8 | 8 | 8 | 8.6667 | 8.5 | 6 | Wong Ying | Desmond, Duc | Through Discussion | Yes | 5 | Excited | 7.8333
| Estimated Task Priority（0-10） |  | 9 | 8 | 9 | 9 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 9 | 8 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 5 | 8 | 6 | 6
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 6 | 7 | 7
2 | Complete Quality Plan | Task Quality Evaluation (After Task Completed) | 8 | 7 | 8 | 9 | 8 | 7 | 8.3333 | 7.6667 | 5.6667 | Jeremy Book | Hussain, Parth | Through Discussion | Yes | 4 | Happy | 7.8333
| Estimated Task Priority（0-10） |  | 9 | 6 | 9 | 9 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 6 | 5 | 8 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 6 | 7 | 8
3 | Application front-end development | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 8 | 8 | 9 | 7.3333 | 8.1667 | 9.3333 | Taneja Parthsarthi | Jeremy, Hussain | Through Discussion | No | - | Sad | 8.3333
| Estimated Task Priority（0-10） |  | 8 | 6 | 7 | 9 | 8 | 6
| Estimated Task Difficulty（0-10） |  | 9 | 7 | 9 | 7 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 8 | 10 | 9 | 9 | 10
| Team Member's Confidence about the Task (0-10) |  | 5 | 6 | 5 | 5 | 5 | 7
4 | Application back-end development | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 8 | 9 | 9 | 8.3333 | 9 | 9.5 | Hussain Khozema Kheriwala | Jeremy, Parth | Through Discussion | No | - | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 9 | 7 | 9 | 10 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 9 | 8 | 9 | 10 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 9 | 10 | 9 | 9 | 10
| Team Member's Confidence about the Task (0-10) |  | 5 | 7 | 5 | 4 | 6 | 7

## TM4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Neutral | Neutral | Sad | Neutral
1 | Revise SRS | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 9.3333 | 6.8333 | 4.6667 | Wong Ying | Desmond, Duc | Through Discussion | Yes | 6 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 8 | 6 | 8 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 5 | 5 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 7 | 8 | 10
2 | Revise Quality Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 8 | 9 | 9 | 9.1667 | 6.6667 | 5 | Jeremy Book | Hussain, Parth | Through Discussion | Yes | 6 | Happy | 8.8333
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 7 | 6 | 8 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 5 | 6 | 6 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 8 | 8 | 10
3 | Update Wiki Page | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 9 | 9 | 9 | 9.3333 | 2.1667 | 1.5 | Ta Anh Duc | - | Allocated by Team Leader | Yes | 1 | Neutral | 9
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 3 | 2 | 1 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 10 | 10 | 10
4 | Develop KCMC Basic Functionality - Book a Movie | Task Quality Evaluation (After Task Completed) | 7 | 8 | 7 | 8 | 8 | 8 | 9 | 8 | 7.5 | Hussain Khozema Kheriwala | Jeremy | Allocated by Team Leader | Yes | 10 | Happy | 7.6667
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 10 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 9 | 7 | 9 | 8 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 8 | 9 | 7 | 6 | 8
| Team Member's Confidence about the Task (0-10) |  | 6 | 7 | 6 | 6 | 7 | 7
5 | Update KCMC UI Design - Home page organisation | Task Quality Evaluation (After Task Completed) | 7 | 9 | 9 | 6 | 8 | 9 | 6.5 | 6.8333 | 8 | Taneja Parthsarthi | Jeremy, Hussain | Allocated by Team Leader | Yes | 10 | Happy | 8
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 9 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 8 | 6 | 6 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 9 | 9 | 9 | 7 | 9
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 9 | 5 | 7 | 7

## TM5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Neutral | Happy | Happy | Neutral
1 | Draft Project Plan | Task Quality Evaluation (After Task Completed) | 8 | 7 | 8 | 8 | 8 | 8 | 9.5 | 6.1667 | 4.8333 | Wong Ying | Duc | Through Discussion | Yes | 5 | Excited | 7.8333
| Estimated Task Priority（0-10） |  | 9 | 9 | 10 | 10 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 7 | 7 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 6 | 4 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 | 5 | 7 | 9
2 | Draft Risk Management Plan | Task Quality Evaluation (After Task Completed) | 8 | 8 | 9 | 8 | 8 | 9 | 9 | 6.1667 | 2.3333 | Taneja Parthsarthi | - | Through Discussion | Yes | 4 | Happy | 8.3333
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 5 | 7 | 6 | 7 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 3 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 9 | 8 | 9
3 | Work further on KCMC Movie Booking | Task Quality Evaluation (After Task Completed) | 8 | 8 | 9 | 9 | 8 | 8 | 9 | 8.1667 | 9.5 | Hussain Khozema Kheriwala | Jeremy, Desmond | Through Discussion | No | - | Happy | 8.3333
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 10 | 9 | 10 | 10 | 8
| Team Member's Confidence about the Task (0-10) |  | 6 | 8 | 9 | 7 | 7 | 7
4 | UI Optimisation | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 6.6667 | 7.1667 | 6.8333 | Desmond Yap | Jeremy, Hussain | Through Discussion | No | - | Excited | 9
| Estimated Task Priority（0-10） |  | 6 | 7 | 6 | 6 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 8 | 7 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 7 | 8 | 7 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 6 | 7 | 7 | 7 | 7 | 6

## TM6
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Wong Ying | Hussain Khozema Kheriwala | Jeremy Book | Desmond Yap | Ta Anh Duc | Taneja Parthsarthi
Team member's mood during the this week's meeting: |  |  | Neutral | Depressed | Depressed | Depressed | Neutral | Neutral
1 | Revise Project Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 8 | 9 | 9 | 8.3333 | 8.1667 | 3.5 | Wong Ying | Duc | Through Discussion | Yes | 3 | Neutral | 8.8333
| Estimated Task Priority（0-10） |  | 9 | 8 | 7 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 9 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 5 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 7 | 8 | 8 | 8 | 8
2 | Revise Risk Management | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 8.6667 | 7.1667 | 2.1667 | Taneja Parthsarthi | - | Through Discussion | Yes | 2 | Happy | 8.8333
| Estimated Task Priority（0-10） |  | 9 | 8 | 9 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 7 | 7 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 3 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 9 | 8 | 9
3 | Update Wiki Page | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.8333 | 1.1667 | 1 | Ta Anh Duc | - | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 8 | 9 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 2 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10 | 10
4 | Develop KCMC Upcoming/Past Booking Page | Task Quality Evaluation (After Task Completed) | 8 | 7 | 8 | 9 | 8 | 7 | 7.3333 | 7.8333 | 7.8333 | Hussain Khozema Kheriwala | Jeremy | Through Discussion | Yes | 8 | Neutral | 7.8333
| Estimated Task Priority（0-10） |  | 6 | 7 | 8 | 8 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 7 | 9 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 8 | 7 | 8 | 9 | 8
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 8 | 7 | 6
5 | Improve UI of Confirmation page and Seat booking page | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 6.8333 | 7.1667 | 4.8333 | Desmond Yap | Jeremy | Through Discussion | Yes | 5 | Happy | 9
| Estimated Task Priority（0-10） |  | 6 | 6 | 7 | 8 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 7 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 4 | 5 | 6 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 8 | 7 | 8